## R1 Changes
Category ID | Description | Est time for fixing/ change for Dev and Testing (Hours) | Complexity | Need clarification from Astona | Classification | Data/Images/ information from Astona | Status | Estimated Date of Completion | Delivered Date
DF-01 | Remove the Symbols "--" from the spinner at crops, vegetables, Animal husbandry, diary | 1 | Simple | Not Required | Defect | No | Completed | 2018-06-22
RC-01 | When user Logins - User should enter User Name and Password ( For First Time only) From second time onwards User should be prompted with 4 Digit Pin Number | 8 | Medium | Required | Requirement Change | No | In Progress | 2018-06-23
CR-01 | Once the Forgot Password activity is completed, user should navigate to Home Screen | 1 | Simple | Not Required | Change Request | No | Completed | 2018-06-22
DF-02 | Responsive design to be implemented across all sizes of Mobiles | 12 | Medium | Not Required | Defect | No | Need to start | 2018-06-26
CR-02 | "Enter Mobile Number" pop up colour should be changed to Orange colour - follow the colour code provided | 1 | Simple | Not Required | Change Request | No | In Progress | 2018-06-22
CR-03 | Background for "Enter mobile Number" pop up should be changed as the image (Transperant Image) will be provided by Astona | 1 | Simple | Required | Change Request | Yes | In Progress | -----
CR-04 | When a user tap on "Back" button, user should navigate to Landing page | 8 | Medium | Not Required | Change Request | No | In Progress | 2018-06-23
DF-03 | Weather display: Location to be calculated by Pin code of location instead of Location Name | 16 | Complex | Not Required | Defect | No | In Progress | 2018-06-27
RC-02 | In Market Prices, user selects State, District and navigates to Commodities/ Vegetables Screens In these screens, display District dropdown as well. so that user can change the district and see the market prices | 4 | Medium | Not Required | Requirement Change | No | In Progress | 2018-06-25
RC-03 | Add a "Back" Button Icon in Commodities/ Vegetables so that user can navigate back to Market Prices page | 1 | Simple | Not Required | Requirement Change | Yes | In Progress | 2018-06-25
CR-05 | Remove logo in Contact screen | 1 | Simple | Not Required | Change Request | No | Completed | 2018-06-22
RC-04 | In Contact screen When user tap on Contact number, user should be able to call the number provided in Contact screen | 1 | Simple | Not Required | Requirement Change | No | Completed | 2018-06-22
RC-05 | In Contact screen When user tap on Email, then user should be able to see the New email opened so that user can fill respective data and send email. Note: to Filed should be filled with provided email Id from the Contact Screen | 1 | Simple | Not Required | Requirement Change | No | Completed | 2018-06-22
CR-06 | Hide Language screen before the Landing Screen | 1 | Simple | Not Required | Change Request | No | Completed | 2018-06-22
CR-07 | In Bottom Navigation: Language button Display the languages as drop down instead of Table text | 1 | Simple | Not Required | Change Request | No | Completed | 2018-06-22
RC-06 | In Landing Screen tiles in the screen should be added with more Six tiles For further usage, design this page as dynamic 6 tiles to be provided by Astona team | 32 | Complex | Not Required | Requirement Change | No | In Progress | ----
CR-08 | Landing screen AGMARKS icon to be moved to the cloud for better display | 1 | Simple | Not Required | Change Request | Yes | Completed | 2018-06-22
CR-09 | In landing page Instead of Loading bar, animate the provided Image like "Zoom In/Out" the provided image | 6 | Simple | Not Required | Change Request | No | Completed | 2018-06-22
CR-10 | In posting, after the Post is success, display as alert | 1 | Simple | Not Required | Change Request | No | In Progress | 2018-06-23
CR-11 | In profile screen: Initially "Edit" button should be displayed, once user Clicks on Edit Display buttons as "Save" Once the user save the button should display as "Edit" Clarification: What should happen when a user clicks "Edit" but with out any change wants to "Cancel "the action Do we need to place the "Cancel" and "Save" button or accept the changes with "Save" button itself | 1 | Simple | Not Required | Change Request | No | In Progress | 2018-06-23
RC-07 | Notification for new feature add in landing page Implementation fo Notifications feature for News, any udpates push by Admin Need to discuss on this feature and document the requirements | 24 | Complex | Required | Requirement Change | No | In Progress | 2018-07-02
DF-04 | When a user Add/Update the options in the Crops, Vegetables, Animal Husbandry and Dairy products, these cahnges should be reflected in "Home" Screen as per the changes in the "Profile" | 8 | Medium | Not Required | Defect | No | In Progress | 2018-06-26
DF-05 | In posting, Reset the Sizes of the Dialog boxes to fit as discussed while user receive post in Postings | 6 | Simple | Not Required | Defect | No | In Progress | 2018-06-27
RC-08 | Registration Forms: While user adding mobile number, please add Country code ex: +91 for India | 12 | Medium | Required | Requirement Change | No | In Progress | 28-06-2018